## LNU
LNU | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget left M28-M36
WP1 | 18 | 10.21 | 3.5 | 21.5 | 11.29 |  | 47.49% | 11.29
WP2 | 4 | 1.1 | -1 | 3 | 1.9 |  | 63.33% | 1.9
WP3 | 4 | 0.73 | -0.5 | 3.5 | 2.77 |  | 79.14% | 2.77
WP4 | 20 | 8.55 | -0.72 | 19.28 | 10.73 |  | 55.65% | 10.73
WP5 | 8 | 1.52 | -2 | 6 | 4.48 |  | 74.67% | 4.48
WP6 | 8 | 1.07 | -2 | 6 | 4.93 |  | 82.17% | 4.93
WP7 | 4 | 0.81 | -1 | 3 | 2.19 |  | 73% | 2.19
WP8 | 3 | 0.75 |  | 3 | 2.25 |  | 75% | 2.25
WP9 | 0 | 0 | 1 | 1 | 1 |  | 100% | 1
Total | 69 | 24.74 | -2.72 | 66.28 | 41.54 |  | 62.67% | 41.54
Re PM Adjustments: (LNU own requests) 1PM from WP2 to WP1; 0.5 PM from WP3 to WP1; 2PM from WP5 to WP1; 2PM from T6.2 to WP4; 1PM from T7.3 transferred to WP9; & See "notes" for SIMPLE for additional Transfer/Reduction of 2,72 PM in WP4
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget left M28-M36
| 69 | 24.74 | -2.72 | 66.28 | 41.54 |  | 62.67% | 41.54
See "notes" for SIMPLE for Reduction of 2,72 PM in WP4
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % used at M27 | Budget (€) remaining @M27
| 528671 | 172742 | -20829.73 | 507841.27 | 335099.27 |  | 65.99% | 335099.27
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 55800 | 10821 | -1845 | 53955 | 43134 |  | 79.94% | 43134
=990 EUR transfer for Ethics Advisor + 855 EUR for AWS to LNU =>Other Direct Costs below=1 845 EUR
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 5000 | 0 | n/a | 5000 | 5000 |  | 100% | 5000
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 5000 | 6339 | 7735.5 | 12735.5 | 6396.5 |  | 50.23% | 6396.5
Add transfers from Partners for AWS (958,50+657+715,50+369 +220,50=2920,50) and Ethics Advisor (990*3= 2970 EUR ) = 5 890,50 EUR
NB: PLUS 1 845 EUR for LNU's own share for AWS (855 EUR ) Ethics Advisor (990 EUR) transferred from LNU travel budget as above.
For Info: Revised Budget at M19
|  |  | Direct Cost | 579531.77
|  |  | OH | 144882.9425
|  |  | Total | 724414.7125

## NKUA
NKUA | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
WP1 | 1 | 0.54 | n/a | 1 | 0.46 |  | 46% | 0.46
WP2 | 6 | 1.42 | n/a | 6 | 4.58 |  | 76.33% | 4.58
WP3 | 9 | 3.38 | -2.19 | 6.81 | 3.43 |  | 50.37% | 3.43
WP4 | 24 | 9.65 | -2.3 | 21.7 | 12.05 |  | 55.53% | 12.05
WP5 | 15 | 8.27 | -2 | 13 | 4.73 |  | 36.38% | 4.73
WP6 | 12 | 5.06 | n/a | 12 | 6.94 |  | 57.83% | 6.94
WP7 | 6 | 1.29 | n/a | 6 | 4.71 |  | 78.5% | 4.71
WP8 | 5 | 0.52 | n/a | 5 | 4.48 |  | 89.6% | 4.48
WP9 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0
Total | 78 | 30.13 | -6.49 | 71.51 | 41.38 |  | 57.87% | 41.38
See Sheet "Notes"
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
| 78 | 30.13 | -6.49 | 71.51 | 41.38 |  | 57.87% | 41.38
See Sheet "Notes"
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % used at M27 | Budget (€) remaining @M27
| 347287 | 132840 | -28912.91 | 318374.09 | 185534.09 |  | 58.28% | 185534.09
See Sheet "Notes"
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 48000 | 19746 | n/a | 48000 | 28254 |  | 58.86% | 28254
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 10000 | 4791 | -990 | 9010 | 4219 |  | 46.83% | 4219
=990 EUR transfer for Ethics Advisor to LNU
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 9000 | 1725 | -958.5 | 8041.5 | 6316.5 |  | 78.55% | 6316.5
=985,50 EUR transfer for AWS to LNU
For Info: Revised Budget at M19
|  |  | Direct Cost | 383425.59
|  |  | OH | 95856.3975
|  |  | Total | 479281.9875

## UGent
UGent | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
WP1 | 1 | 0.28 | n/a | 1 | 0.72 |  | 72% | 0.72
WP2 | 6 | 0 | n/a | 6 | 6 |  | 100% | 6
WP3 | 10 | 2.08 | n/a | 10 | 7.92 |  | 79.2% | 7.92
WP4 | 0.5 | 0 | n/a | 0.5 | 0.5 |  | 100% | 0.5
WP5 | 9 | 0.9 | n/a | 9 | 8.1 |  | 90% | 8.1
WP6 | 17 | 9.15 | n/a | 17 | 7.85 |  | 46.18% | 7.85
WP7 | 6 | 0.04 | n/a | 6 | 5.96 |  | 99.33% | 5.96
WP8 | 4 | 0.31 | n/a | 4 | 3.69 |  | 92.25% | 3.69
WP9 | 0 | 0 | n/a | 0 | 0 | 0 | 0 | 0
Total | 53.5 | 12.76 |  | 53.5 | 40.74 |  | 76.15% | 40.74
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
| 53.5 | 12.76 | 0 | 53.5 | 40.74 | 0 | 76.15% | 40.74
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 248877 | 134012 | n/a | 248877 | 114865 |  | 46.15% | 114865
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 21600 | 3223 | n/a | 21600 | 18377 |  | 85.08% | 18377
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 0 | 0 | 0 | n/a | n/a | n/a | n/a | n/a
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 15000 | 2511 | 1647 | 13353 | 10842 |  | 81.2% | 10842
=990 EUR transfer for Ethics Advisor to LNU
=657 EUR transfer for AWS to LNU
For Info: Revised Budget at M19
|  |  | Direct Cost | 283830
|  |  | OH | 70957.5
|  |  | Total | 354787.5

## NTNU
NTNU | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
WP1 | 1 | 1 | n/a | 1 | 0 |  | 0% | 0
WP2 | 16 | 9.59 | n/a | 16 | 6.41 |  | 40.06% | 6.41
WP3 | 8 | 2.71 | n/a | 8 | 5.29 |  | 66.12% | 5.29
WP4 | 8 | 4.35 | n/a | 8 | 3.65 |  | 45.62% | 3.65
WP5 | 8 | 3.15 | n/a | 8 | 4.85 |  | 60.62% | 4.85
WP6 | 8 | 2.66 | n/a | 8 | 5.34 |  | 66.75% | 5.34
WP7 | 6 | 2.95 | n/a | 6 | 3.05 |  | 50.83% | 3.05
WP8 | 3 | 0.41 | n/a | 3 | 2.59 |  | 86.33% | 2.59
WP9 | 0 | 0 | n/a | 0 | 0 |  | 0% | 0
Total | 58 | 26.82 |  | 58 | 31.18 |  | 53.76% | 31.18
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
| 58 | 26.82 | n/a | 58 | 31.18 | 0 | 53.76% | 31.18
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 373659 | 155586 | n/a | 373659 | 218073 |  | 58.36% | 218073
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 15000 | 1743 | n/a | 15000 | 13257 |  | 88.38% | 13257
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 0 | 0 | n/a | n/a | n/a | n/a | n/a | n/a
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 11000 | 0 | -1705.5 | 9294.5 | 9294.5 |  | 100% | 9294.5
=990 EUR transfer for Ethics Advisor to LNU
=715,50 EUR transfer for AWS to LNU
For Info: Revised Budget at M19
|  |  | Direct Cost | 397953.5
|  |  | OH | 99488.375
|  |  | Total | 497441.875

## TCD
TCD | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
WP1 | 1 | 0.5 | n/a | 1 | 0.5 |  | 50% | 0.5
WP2 | 4 | 1 | -2 | 2 | 1 |  | 50% | 1
WP3 | 2 | 1 | n/a | 2 | 1 |  | 50% | 1
WP4 | 2 | 0.5 | n/a | 2 | 1.5 |  | 75% | 1.5
WP5 | 5 | 0.5 | n/a | 5 | 4.5 |  | 90% | 4.5
WP6 | 3 | 3 | n/a | 3 | 0 |  | 0% | 0
WP7 | 12 | 7 | n/a | 12 | 5 |  | 41.67% | 5
WP8 | 1 | 0.5 | n/a | 1 | 0.5 |  | 50% | 0.5
WP9 | 0 | 1 | 2 | 2 | 1 |  | 50% | 1
Total | 30 | 15 | 0 | 30 | 15 |  | 50% | 15
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
| 30 | 15 | 0 | 30 | 15 | 0 | 50% | 15
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 261480 | 126536 | n/a | 261480 | 134944 |  | 51.61% | 134944
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 20000 | 8440 | n/a | 20000 | 11560 |  | 57.8% | 11560
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 500 | 0 | -369 | 131 | 131 |  | 100% | 131
= 369 EUR transfer for AWS to LNU
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 500 | 0 | n/a | 500 | 500 |  | 100% | 500
For Info: Revised Budget at M19
|  |  | Direct Cost | 282111
|  |  | OH | 70527.75
|  |  | Total | 352638.75

## SIMPLE
SIMPLE | [5 empty] | NOTE: Figures in columns H&I will change automatically when figures are added in column G
Person Months Summary (PM)
WP# | Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
WP1 | 0 | 0
WP2 | 0 | 0
WP3 | 3 | 0 | 2 | 5 | 5 |  | 100% | 5
WP4 | 12 | 10 | 7.5 | 17.5 | 7.5 |  | 42.86% | 7.5
WP5 | 3 | 0 | 2.5 | 5.5 | 5.5 |  | 100% | 5.5
WP6 | 0 | 0
WP7 | 0 | 0
WP8 | 0 | 0
WP9 | 0 | 0
Total | 18 | 10 | 12 | 28 | 18 |  | 64.29% | 18
Person Months Summary (PM)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | PM Budget remaining @M19 | Actual PM M19-M27 | % left at M27 | PM Budget remaining @M27
| 18 | 10 | 12 | 28 | 18 |  | 64.29% | 18
Direct Costs: Personnel (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 55734 | 41452 | 49742.64 | 105476.64 | 64024.64 |  | 60.7% | 64024.64
Direct Costs: Travel and Subsistence (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 12000 | 4699 | n/a | 12000 | 7301 |  | 60.84% | 7301
Direct Costs: Equipment (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 22000 | 3084 | -220.5 | 21779.5 | 18695.5 |  | 85.84% | 18695.5
=220,50 EUR transfer for AWS to LNU
Direct Costs: Other Goods Works and Services (€)
| Plan M1-M36 | Actual M1-M18 | Adjustment (if applicable) | Budget after Revisions at M19 | Budget (€) remaining @M19 | Actual (€) M19-M27 | % left at M27 | Budget (€) remaining @M27
| 2000 | 435 | n/a | 2000 | 1565 |  | 78.25% | 1565
For Info: Revised Budget at M19
|  |  | Direct Cost | 141256.14
|  |  | OH | 35314.035
|  |  | Total | 176570.175

## Notes
Transfers Between SIMPLE / LNU / NKUA
PM Rate at Project Start
LNU= 528 671 / 69 PM = 7 661,90 EUR
NKUA= 347 287 / 78 PM = 4 452,40 EUR
SIMPLE = PM = 4 145,22 EUR (SME)
Transfer 1 to SIMPLE (7,5 PM)
Transfer of 7,5 PM= 4 145,22 EUR *7.5 PM = 31 089,15 EUR
25% OH = 7 772,28
Total Transfer = 38 861,44 EUR
|  |  | Direct Cost | OH | Total | PM | WP
SIMPLE = 31 089,15 Direct Personnel Cost = 7,5 PM |  |  | 31089.15 | 7772.2875 | 38861.4375 | 7.5 | 4
LNU= 20829 | Direct Personnel Cost | 2,71 PM | 20829.73 | 5207.4325 | 26037.16 | 2.7186 | 4
NKUA= 12 824 Direct Personnel Cost |  | 2,88PM | 10259.42 | 2564.855 | 12824.27 | 2.3042 | 4
Transfer 2 to SIMPLE (4,5 PM)
Transfer of 4,5 PM= 4 145,22 EUR *4.5 PM = 18 653,49 EUR
25% OH = 4 663,37
Total Transfer = 23 316,86 EUR
|  |  | Direct Cost | OH | Total | PM | WP
SIMPLE = 18 653,49 Direct Personnel Cost = 4,5 PM |  |  | 18653.49 | 4663.3725 | 23316.8625 | 4.5 | 2 PM =WP3; 2.5 PM = WP5
NKUA= 18 653,49 Direct Personnel Cost |  | =4,19 PM | 18653.49 | 4663.3725 | 23316.8625 | 4.1895 | 2,19 PM =WP3; 2 PM = WP5
For earlier PM Adjustments requested by partners between WPs see this excel sheet
https://docs.google.com/spreadsheets/d/1pjkCHLR4sPtML0BspdUpSIApHw3yBlVIuFKTWZjv-pc/edit?pli=1&gid=1653067912#gid=1653067912